## Guidelines
Naico ITS Weekly Status Report Template
Weekly Status Report Usage Guidelines
Remove the Guidelines sheet when this template is copied to a Project SVN for use in Project. This sheet should not be present in the WSR shared with client.
WSR - Weekly Status Report
It is not mandatory to use this template for all projects although it is reccommended.
Sharing WSR in the form of Project Plan and Sprint Plan covering the same amount of details should be fine, if that will reduce the over head.
Criticality is on periodically sharing with client all the informations covered in this report. Whether this report is used or the information is shared in another format is not an issue.
Rev | Date of Revision | Description of Change | Created By
1.0 | 2011-07-18 | First Version of WSR Template created | Yahya E Pareed

## WeeklyStatusReport
MKC WIRAS Monitoring Solution Weekly Status Report for Jan 03 2022 to Jan 07 2022
Actual / Potential Risks to Project Cost and Schedule
S No | Risk Description |  | Risk Impact |  |  | Status | Naico Actions and Remarks
1 | Installation of power supply for Sensors and Edge devices |  | Long distance will have reduction in current which in turn will impact data passed to App |  |  | OPEN | Based on site visit, Naico will be providing a proper plan on the Installation details
2 | Identifying water level in Pond and Well |  | Identifying right sensors and installing it in right place to get proper water level |  |  | OPEN | Naico is currently getting quotes and installation details fom different vendors for checking water level, once the vendor is identified, proper installation will be identified
3 | Proper network availability near sensor installations |  | With current details collected, we need to have the network availability within 100 meters |  |  | OPEN | Based on site visit, if the ethernet connectivity is not possible in 100 meters, Naico will be finding alternate options and updating MKC accordingly
Activities Planned and Executed in the Last Week
Sl. No: | Activity Description | Start Date | End Date | Current Status | Remarks
1 | Requirement Discussion | 2022-01-03 | 2022-01-13 | In Progress | Once the activity is completed, Naico will be delivering a proper requirement document with all the details
2 | Identifying proper sensors | 2022-01-03 | 2022-01-13 | In Progress
3 | Learning Sensor installations | 2022-01-03 | 2022-01-13 | In Progress | In process of identifying right vendor and getting all the details
4 | Identifying risks and doscumenting | 2022-01-03 | 2022-01-13 | In Progress
5 | UI/UX Wireframe design | 2022-01-03 | 2022-01-13 | In Progress | Once the activity is completed, Naico will be delivering UI/UX wireframe to MKC
Activities Planned for This Week
Sl. No: | Planned Item Description | Start | End | Remarks
1 | Requirement Discussion | 2022-01-03 | 2022-01-13
2 | Identifying proper sensors | 2022-01-03 | 2022-01-13
3 | Learning Sensor installations | 2022-01-03 | 2022-01-13
4 | Identifying risks and doscumenting | 2022-01-03 | 2022-01-13
5 | UI/UX Wireframe design | 2022-01-03 | 2022-01-13
5 | Preparing Project Plan | 2022-01-10 | 2022-01-13
Areas of Concern if any
Naico is collecting details and quotes fom different vendors for sensors, once the vendor is identified, will have a site visit. Tentatively planning for Jan 18 or Jan 19
Other Communications if any (Upcoming Naico Holidays, Lead's Upcoming Leave Plan etc.)
Jan 26, 2022 is Republic Day and Naico team have Holiday
Project Milestone Summary (If project duration more than 3 months list the milestones targeted for next 3 months)
Sl. No: | Milestone Description | Planned Date | Revised Date | Actual Date | Status | Risk Level | Client Dependencies for the Milestone
1 | Requirement Gathering | 2022-01-14 |  |  | ON PLAN | HIGH
2 | Arichitucture Design | 2022-01-28 |  |  | ON PLAN | MEDIUM
3 | App Development Sprint 1 | 2022-02-11 |  |  | ON PLAN | MEDIUM
4 | App Development Sprint 2 | 2021-02-25 |  |  | ON PLAN | MEDIUM
5 | Set Up and System Integration | 2022-03-25 |  |  | ON PLAN | VERY HIGH | Need to be implemeted in client site
6 | System Testting | 2022-04-15 |  |  | ON PLAN | HIGH
7 | Deployment, Acceptance & Closure | 2022-04-29 |  |  | ON PLAN | NONE