## WeeklyStatusReport
MKC WIRAS Monitoring Solution Weekly Status Report for Jan 10 2022 to Jan 14 2022
Actual / Potential Risks to Project Cost and Schedule
S No | Risk Description |  | Risk Impact |  |  | Status | Naico Actions and Remarks
1 | Installation of power supply for Sensors and Edge devices |  | Long distance will have reduction in current which in turn will impact data passed to App |  |  | OPEN | Based on site visit, Naico will be providing a proper plan on the Installation details
2 | Identifying water level in Pond and Well |  | Identifying right sensors and installing it in right place to get proper water level |  |  | OPEN | Naico is currently getting quotes and installation details fom different vendors for checking water level, once the vendor is identified, proper installation will be identified
3 | Proper network availability near sensor installations |  | With current details collected, we need to have the network availability within 100 meters |  |  | OPEN | Based on site visit, if the ethernet connectivity is not possible in 100 meters, Naico will be finding alternate options and updating MKC accordingly
Activities Planned and Executed in the Last Week
Sl. No: | Activity Description | Start Date | End Date | Current Status | Remarks
1 | Requirement Discussion | 2022-01-03 | 2022-01-19 | In Progress | 85% of the document is completed and final review needs to be completed
2 | Identifying proper sensors | 2022-01-03 | 2022-01-13 | In Progress | This is being partially completed and final decision can be made after site visit
3 | Learning Sensor installations | 2022-01-03 | 2022-01-13 | In Progress | Completed and final decision will be made after site visit
4 | Identifying risks and doscumenting | 2022-01-03 | 2022-01-13 | Open
5 | UI/UX Wireframe design | 2022-01-03 | 2022-01-18 | In Progress | Completed and final review is pending
Activities Planned for This Week
Sl. No: | Planned Item Description | Start | End | Remarks
1 | Requirement Discussion | 2022-01-03 | 2022-01-21 | Will be finalizing this week
2 | Identifying proper sensors | 2022-01-03 | 2022-01-21 | Will be finalizing this week
3 | Identifying risks and doscumenting | 2022-01-03 | 2022-01-13 | Ongoing activity till development starts
4 | UI/UX Wireframe design | 2022-01-03 | 2022-01-19 | Completed and pending for final revierw
5 | Preparing Project Plan | 2022-01-10 | 2022-01-21 | Will get it completed this week
Areas of Concern if any
Decided that Naico will have the site visit on Jan 19, 2022
Other Communications if any (Upcoming Naico Holidays, Lead's Upcoming Leave Plan etc.)
Jan 26, 2022 is Republic Day and Naico team have Holiday
Project Milestone Summary (If project duration more than 3 months list the milestones targeted for next 3 months)
Sl. No: | Milestone Description | Planned Date | Revised Date | Actual Date | Status | Risk Level | Client Dependencies for the Milestone
1 | Requirement Gathering | 2022-01-14 |  |  | ON PLAN | HIGH
2 | Arichitucture Design | 2022-01-28 |  |  | ON PLAN | MEDIUM
3 | App Development Sprint 1 | 2022-02-11 |  |  | ON PLAN | MEDIUM
4 | App Development Sprint 2 | 2021-02-25 |  |  | ON PLAN | MEDIUM
5 | Set Up and System Integration | 2022-03-25 |  |  | ON PLAN | VERY HIGH | Need to be implemeted in client site
6 | System Testting | 2022-04-15 |  |  | ON PLAN | HIGH
7 | Deployment, Acceptance & Closure | 2022-04-29 |  |  | ON PLAN | NONE