## WeeklyStatusReport
MKC WIRAS Monitoring Solution Weekly Status Report for Mar 28 2022 to Apr 01 2022
Actual / Potential Risks to Project Cost and Schedule
S No | Risk Description |  | Risk Impact |  |  | Status | Naico Actions and Remarks
1 | Installation of power supply for Sensors and Edge devices |  | Long distance will have reduction in current which in turn will impact data passed to App |  |  | MITIGATED | Based on site visit, Naico will be providing a proper plan on the Installation details
2 | Identifying water level in Pond and Well |  | Identifying right sensors and installing it in right place to get proper water level |  |  | MITIGATED | Naico is currently getting quotes and installation details fom different vendors for checking water level, once the vendor is identified, proper installation will be identified 24/01 - Naico require some updates from MKC to complete the entire requirement of identifying water level 14/02 - We got all the informations required
3 | Proper network availability near sensor installations |  | With current details collected, we need to have the network availability within 100 meters |  |  | MITIGATED | Based on site visit, if the ethernet connectivity is not possible in 100 meters, Naico will be finding alternate options and updating MKC accordingly 24/01 - Seems like there were near by buildings where ether net connectivity is possible
4 | Software Infrastructure Purchase confirmation |  | Schedule deviation and delay in development as we have to finalize the architecture |  |  | MITIGATED | Waiting for the confirmation from MKC to use the right cloud hosting platform 14/02 - Descided to go with Azure cloud hosting platform
5 | Hardware Purchase confirmation |  | Need to have all the sensor and related equipments purchased in another one week to keep the schedule on time |  |  | MITIGATED | Waiting response from MKC on this regard 28/02 - Had a discussion regarding the same, Naico have recirculated the vendor information to MKC 18/03 - Got approval from MKC to purchase harware part on behalf of MKC and currently preparing preparing purchase order and related procurements
Activities Planned and Executed in the Last Week
Sl. No: | Activity Description | Start Date | End Date | Current Status | Remarks
1 | Completed Sprint 1 with Basic UI screens including Login and user modules | 2022-02-14 | 2022-02-25 | Implemented
2 | Setting up Azure Cloud hosting infrastructure based on confirmation from MKC | 2022-02-14 | 2022-02-25 | Implemented
3 | Development Sprint 2 | 2022-02-14 | 2022-02-25 | Implemented
4 | Development Sprint 3 | 2022-02-28 | 2022-04-01 | Implemented | Web development completed and only device intergration pending
5 | Hardware Procurement |  |  | In Progress | Payment for the all of the vendors completed, received Ethernet Modbus Gateway
Activities Planned for This Week
Sl. No: | Planned Item Description | Start | End | Remarks
1 | Hardware Procurement |  |  | Payment for the all of the vendors completed. Waiting for rest of the sensors
Areas of Concern if any
Other Communications if any (Upcoming Naico Holidays, Lead's Upcoming Leave Plan etc.)
Project Milestone Summary (If project duration more than 3 months list the milestones targeted for next 3 months)
Sl. No: | Milestone Description | Planned Date | Revised Date | Actual Date | Status | Risk Level | Client Dependencies for the Milestone
1 | Requirement Gathering | 2022-01-14 |  |  | ON PLAN | HIGH
2 | Arichitucture Design | 2022-01-28 |  |  | ON PLAN | MEDIUM
3 | App Development Sprint 1 | 2022-02-11 |  |  | ON PLAN | MEDIUM
4 | App Development Sprint 2 | 2021-02-25 |  |  | ON PLAN | MEDIUM
5 | Set Up and System Integration | 2022-03-25 |  |  | ON PLAN | VERY HIGH | Need to be implemeted in client site
6 | System Testting | 2022-04-15 |  |  | ON PLAN | HIGH
7 | Deployment, Acceptance & Closure | 2022-04-29 |  |  | ON PLAN | NONE