## Guidelines
Naico ITS Function Point Estimation Template
WBS Estimation Template Usage Guidelines
Estimation Sheet
Only function points should be added in the estimation. No need to consider technical. Estimation should be categorized as Category, Group and Detailed Requirement
The category should be the different modules, group should be the feature and the detailed requirement should be the different items. The Group to be defined in such a way that the distinct list from the group will be the feature list in the application
Adjustment Factor - This sheet contains various factors which will impact the whole project. Select appropriate values from drop down for each factor. Any item which is not available in the AdjustmentFactor should be informed to the proposal owner, so that a process improvement request can be raised and the same can be added to the template with proper weightage
In 'Estimate' worksheet, the user can write additional points such as 'constraints', 'assumptions', 'out of scope' and 'technical notes'. There will be prefix assigned for each sections such as 'C' for 'Constraints', 'A' for Assumptions, 'O' for 'Out of scope' conditions and 'T' for technical notes. User can enter the text after specifying the prefix. For E.g: 'O - Patient Information records will not be shared along with employee database'
Once the estimation is reviewed and finalized, the ResourcePlanning along with the Schedule & Deliverables can be added
Revision History
Rev | Date of Revision | Description of Change | Created By
1.0 | 2018-01-09 | First version of WBS bassed estimate template with Schedule and deliverables. This can be a bsic template to be filled by the technical team for smallproject as part of the proposal preparation | Nishad Hassan
1.1 | 2019-05-02 | Modified after review by bringing complexity risk etc. Also reviewing the overhead elements and options to match with latest technology and practices | Nishad Hassan
1.2 | 2019-07-19 | Added the guidelines Cleared the Schedul&Deliverables sheet and added notes in Schedul&Deliverables and Resource Planning Added sample data in the estimates sheet | Jose Francis K J
1.3 | 2020-04-01 | *Added 1 column 'Requirement' in Estimate worksheet. *Added 'Deployment' with 5% value in the overheads section. *Contraints, Assumptions, Technical Notes and 'Out of scope' is integrated in 1 column in 'Estimate' worksheet *Added 'Reviewed By' column in Revision history table in 'Estimate' worksheet | Deepak Venugopal
1.4 | 2021-05-05 | Made lot of modifications | Rajesh Kummil
1.5 | 2021-06-14 | Feedback Integration | Rajesh Kummil
1.6 | 2021-06-15 | Feedback Integration | Rajesh Kummil
1.7 | 2021-06-30 | Feedback Integration | Rajesh Kummil

## Estimate
No | Module/ Category | Epic/ Feature | User Stories/ Requirement | Detailed Requirement | Size | Complexity | Risk / Uncertainity | Count | Hours | Low Test Case Count | Medium Test Case Count | High Test Case Count | Type( C - 'Constraints', A - 'Assumptions', O - 'Out of Scope' T - 'Technical Notes') | Remarks
Web Side
1 | Project Initial Design and Architecture Setup |  | Frontend | Frontend | Medium | Normal | Normal | 1 | 8 |  |  | 1 | A - Change in the estimated hours depending upon the resources and technologies.
|  |  | Backend | Backend | Medium | Normal | Normal | 1 | 8 |  |  | 1 | A - Estimated using Node Js and Mongo DB (Backend) and Angular or React (Front end)
A - Estimation is calculated for development only.
Communication with Embedded Device
|  |  | Api Endpoints |  | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Create Standard Models (Incoming Data from the device) |  | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  | Data Format of the sensor readings | [9 empty] | 1
|  |  | Read Data from the device |  | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Generate Json From String |  | Medium | Normal | Normal | 1 | 8 | 0 | 0 | 1
|  |  | Save Data Database |  | Medium | Normal | Normal | 1 | 8 | 0 | 0 | 1
2 | Admin User Module
|  | Login | Admin User Login | Creating filter(Authentication Token) | Medium | Normal | Normal | 1 | 8 | 0 | 0 | 1
|  |  |  | API | Small | Normal | Normal | 1 | 4 | 0 | 0 | 1
|  |  |  | UI | Small | Normal | Normal | 1 | 4 | 1 | 0 | 1
|  | Dashboard | Admin dashboard | Listing Tenants and users | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Show Detailed View | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  | Profile Page | Adim Profile Page | Update Email Id | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  |  | Generate Reset Password Link | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  |  | Reset Password | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 2
|  | User Management | Manage Tenant Users | Add | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  |  |  | Edit | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  |  |  | Delete | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Manage the Tenant facility | Add | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  |  |  | Edit | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  |  |  | Delete | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  |  | View Page | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Assign Tenant Facility to User | Assign Facility page | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  | Information about Installed Sensors/ Devices | Manage information about Installed Sensors/ Devices | Add | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  |  |  | Edit | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  |  |  | Delete | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  |  | View Sensors/Devices | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
3 | Logout(common)
|  | For All users | Logout | Logout | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
4 | Tenant User Module
|  | Login | Tenant User Login | login | Small | Normal | Normal | 1 | 4 | 1 | 0 | 1
|  | Dashboard | Tenant User Dashboard | Water Level(Tank) | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  |  | Power Meter Reading | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  | Profile Page | Profile Page - Tenant User | Update Email and Password | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  | Change Password | Change Password Request to Admin | Change Password request(Email) | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
5 | Power Resource Management
|  | Dashboard & Reports | Power Consumption - Campus | View Total Usage | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 1 | 0 | 2
|  |  |  | View Usage by Tenant | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 1 | 0 | 2
|  |  | Power Consumption - Tenant wise | View Power Consumption by Tenant Wise | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | API | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 1 | 0 | 2
|  |  | Power Consumption - Block wise (Each tenant) | View Power Consumption by Block wise | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | API | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 1 | 0 | 1
|  |  | Comparison with allocated load (% of power consumption) | View Load Comparison | Large | Normal | Normal | 1 | 12 | 0 | 1 | 2
|  |  |  | API | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 1 | 0 | 2
|  |  | Export Option | Power Consumption by block | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  |  | Power Consumption by tenant | Small | Normal | Normal | 1 | 4 | 1 | 0 | 1
|  |  |  | Usage by tenants | Small | Normal | Normal | 1 | 4 | 1 | 0 | 1
|  |  |  | Total usage | Small | Normal | Normal | 1 | 4 | 1 | 0 | 2
6 | Water Resource Management
|  | Dashboard & Reports | Water availablity -Campus | View Water Availability | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 0 | 0 | 2
|  |  | Water availability - Tenant wise | View Availabiltiy by Tenant | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 0 | 0 | 2
|  |  | Consumption - Tenant wise | View Consumption by tenant | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 0 | 0 | 2
|  |  | Consumption (Drill Down Block wise) | View Blockwise Consumption | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Filter and Search | Small | Normal | Normal | 1 | 4 | 0 | 0 | 2
|  |  | Availability forcast | UI Design (Live forecast widget) | Small | Normal | Normal | 1 | 4 | 0 | 0 | 1
|  |  |  | API | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  |  | Frontend | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Export Option | Water Resource Consumption by block | Small | Normal | Normal | 1 | 4 | 0 | 0 | 1
|  |  |  | Water Resource Consumption by tenant | Small | Normal | Normal | 1 | 4 | 0 | 0 | 1
|  |  |  | Usage by tenants | Small | Normal | Normal | 1 | 4 | 0 | 0 | 1
|  |  |  | Total usage | Small | Normal | Normal | 1 | 4 | 0 | 0 | 2
7 | Sewage Treatment Plant Management
Dashboard & Reports
|  |  | Treatment capacity available | view the quantity | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | % of treatment capacity utilised | view the % capacity | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Availability of treated water | view the quantity | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Water quality monitoring | view the pH, Turbidity, TDS, COD & BOD level | Large | Medium | Normal | 1 | 15 | 0 | 1 | 1
Embedded Side
1 | Initial Setup | [11 empty] | A - Change in the estimated hours depending upon the resources and format of the output of the sensors (endians).
|  | Selecting Microcontroller | [10 empty] | A - Hardware design estimations is not done.
|  |  | Selecting the microcontroller | Collecting Number of Inputs | Extra Small | Normal | Normal | 1 | 2 | 1 | 0 | 0 | A - Trying to get a single module from the market to interface the sensors which contain the microcontroller also.
|  |  |  | Selecting the microcontroller according to the number of inputs | Small | Normal | Normal | 1 | 4 | 1 | 0 | 0 | A - If the module is not available then the estimation will increase to design the hardware.
|  | Setup the Embedded device board | [10 empty] | A - Estimation is calculated for development only.
|  |  | Setup the embedded board for reading datas from the sensors | Setup the power source | Small | Normal | Normal | 1 | 4 | 1 | 0 | 0 | A - Not included estimation of Unit testing and qa testing.
|  |  |  | Intialise the Board | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 0
|  |  |  | Check the Serial Ports | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 0
|  |  | Communication between sensors and microcontrollers using RS-485 interface | Check the power consumption of the sensors | Small | Normal | Normal | 1 | 4 | 1 | 0 | 0
|  |  |  | Check the working of sensors serially | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 0
2 | MQTT Implementation
|  | Mosquitto Broker Setup and Client configurations | Mosquitto broker installation and setup | Mosquitto broker installation and setup | Medium | Normal | Normal | 1 | 8 | 0 | 1 | 0
|  |  | Device Authentication setup on Mosquitto broker | Device Authentication setup on Mosquitto broker | Large | Medium | Normal | 1 | 15 | 0 | 1 | 0
|  |  | Certificate creation and management | Certificate creation and management | Medium | Medium | Normal | 1 | 10 | 0 | 1 | 0
|  |  | MQTT topic creation and management | MQTT topic creation and management | Large | Normal | Normal | 1 | 12 | 0 | 1 | 0
|  |  | MQTT topic access and subcription | MQTT topic access and subcription | Medium | Normal | Normal | 1 | 8 | 0 | 1 | 0
|  |  | MQTT Authentication setup on the Device | MQTT Authentication setup on the Device | Large | Normal | Normal | 1 | 12 | 0 | 1 | 0
|  |  | MQTT Topic managemnt on device | MQTT Topic managemnt on device | Medium | Normal | Normal | 1 | 8 | 0 | 1 | 0
|  | MQTT Replacing API's | MQTT Device API changes | MQTT Device API changes | Small | Normal | Normal | 1 | 4 | 0 | 1 | 0
|  |  | MQTT server API changes | MQTT server API changes | Small | Normal | Normal | 1 | 4 | 0 | 1 | 0
3 | Power Resources Management
Smart Energy Meter
|  |  | Interfacing smart meter interface with microcontroller serially | Interfacing smart meter interface with microcontroller serially | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Collecting load capacity data from the sensor | Collecting load capacity data from the sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Collecting allocated load for each tenant | Collecting allocated load for each tenant | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Formatting the data from the meter | Formatting the data from the meter | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Communication with the server | Communication with the server | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
4 | Water Resources Management
Digital Flow Meter Sensor
|  |  | Interfacing Flow Meter Sensor interface with microcontroller serially | Interfacing Flow Meter Sensor interface with microcontroller serially | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Collecting water capacity data from the sensor | Collecting water capacity data from the sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Collecting allocated water capacity for each tenant | Collecting allocated water capacity for each tenant | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Formatting the data from the Flow Meter Sensor | Formatting the data from the Flow Meter Sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Communication with the server | Communication with the server | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
Water Level Sensor
|  |  | Interfacing Water Level Sensor interface with microcontroller serially | Interfacing Water Level Sensor interface with microcontroller serially | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Collecting water level data from the sensor | Collecting water level data from the sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Collecting total water capacity in the source | Collecting total water capacity in the source | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Formatting the data from the Water Level Sensor | Formatting the data from the Water Level Sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Communication with the server | Communication with the server | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
Ph Sensor
|  |  | Interfacing Ph Sensor interface with microcontroller serially | Interfacing Ph Sensor interface with microcontroller serially | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Collecting Ph level data from the sensor | Collecting Ph level data from the sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Collecting Ph level of the water | Collecting Ph level of the water | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Formatting the data from the Ph Sensor | Formatting the data from the Ph Sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Communication with the server | Communication with the server | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
Turbidity Sensor
|  |  | Interfacing Turbidity Sensor interface with microcontroller serially | Interfacing Turbidity Sensor interface with microcontroller serially | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Collecting Turbidity level data from the sensor | Collecting Turbidity level data from the sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Collecting Turbidity level of the water | Collecting Turbidity level of the water | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Formatting the data from the Turbidity Sensor | Formatting the data from the Turbidity Sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Communication with the server | Communication with the server | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
TDS Sensor
|  |  | Interfacing TDS Sensor interface with microcontroller serially | Interfacing TDS Sensor interface with microcontroller serially | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Collecting TDS level data from the sensor | Collecting TDS level data from the sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Collecting TDS level of the water | Collecting TDS level of the water | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Formatting the data from the TDS Sensor | Formatting the data from the TDS Sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Communication with the server | Communication with the server | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
COD and BOD Sensor
|  |  | Interfacing COD and BOD Sensor interface with microcontroller serially | Interfacing COD and BOD Sensor interface with microcontroller serially | Medium | Normal | Normal | 1 | 8 | 1 | 0 | 1
|  |  | Collecting COD and BOD level data from the sensor | Collecting COD and BOD level data from the sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Collecting COD and BOD level of the water | Collecting COD and BOD level of the water | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Formatting the data from the COD and BOD Sensor | Formatting the data from the COD and BOD Sensor | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  |  | Communication with the server | Communication with the server | Large | Normal | Normal | 1 | 12 | 0 | 1 | 1
|  | Total | [6 empty] | 1090 | 42 | 63 | 125
Any additional items outside overhead and adjustment factors
| 0% |  | Development Overhead | [5 empty] | 363.3333
| 0% | [7 empty] | 0
| 0% | [7 empty] | 0
| 0% | [7 empty] | 0
| 0% | [7 empty] | 0
|  | Total Dev | [6 empty] | 1453.3333
Additional QA Test Case counts in various stages
| 50% | Integration Testing | Considering 50% of Functional Testing test cases | [6 empty] | 21 | 31.5 | 62.5
| 35% | System Testing | Considering 35% of Functional Testing test cases | [6 empty] | 14.7 | 22.05 | 43.75
| 35% | UAT | Considering 35% of System Testing test cases | [6 empty] | 5.145 | 7.7175 | 15.3125
| 50% | Regression Testing | Considering 50% of System Testing test cases | [6 empty] | 7.35 | 11.025 | 21.875
QA Work Breakdown Structure
| 1 | Functional Testing Prep | [6 empty] | 61.2667
| 1 | Functional Testing Exec | [6 empty] | 83.15
| 1 | Integration Testing Prep | [6 empty] | 14.7917
| 3 | Integration Testing Exec | [6 empty] | 83.5
| 1 | System Testing Prep | [6 empty] | 10.3542
| 3 | System Testing Exec | [6 empty] | 58.45
| 1 | UAT Prep | [6 empty] | 3.624
| 1 | UAT Exec | [6 empty] | 6.8192
| 1 | Regression Testing Prep | [6 empty] | 5.1771
| 4 | Regression Testing Exec | [6 empty] | 38.9667
| 4 | Client Feedback Testing | [6 empty] | 8
| 20% | Defect Retesting | Considering 20% of System testing | [5 empty] | 11.69
Security Testing
Stress Testing
|  | Total QA | [6 empty] | 385.7894 | 26.5451
Overheads & Adjustment Factors
|  | Requirement | [6 empty] | 84
|  | Architucture | [6 empty] | 58
|  | HLD | [6 empty] | 80
|  | LLD | [6 empty] | 0
|  | Development | [6 empty] | 125
|  | Deployment | [6 empty] | 72
|  | Grand Total | [6 empty] | 2258.1227
Revision History
Rev | Date of Revision | Done By | Reviewed By | Description of Change | Hours
1.0 | 23/12/2021 | Ramesh K P |  |  | 2258
1.1
1.2

## ResourcePlan
Rough Resource Plan based on Estimates
Select Month / Week | Wk | 40
Target Currency | QR | 3.64
|  | Requirement |  | Design |  | Development | [5 empty] | Stress Testing | Live Release
Role | Hourly Rate | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Total Wk | TOTAL EFFORT HRS | Cost USD | Cost QR | % Share
PM | 30 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 80 | 2400 | 8736 | 37.04%
Architect | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Junior Developer | 22 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 40 | 880 | 3203.2 | 18.52%
Full Stack Developer | 24 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 40 | 960 | 3494.4 | 18.52%
WebDeveloper | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Senior Developer | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Graphic Designer | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 40 | 880 | 3203.2 | 18.52%
QA Lead | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
QA Engineer | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
SEO Expert | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 16 | 0 | 0 | 7.407%
Deployment Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Total |  | 1.2 | 1.2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 5.4 | 216 | 5120 | 18636.8 | 100%
Risk | 5% | [13 empty] | 10.8 | 256 | 931.84
Warranty | 5% | [13 empty] | 10.8 | 256 | 931.84
Timeline Escalation Allow. | 0% | [13 empty] | 0 | 0 | 0
Penalty for delivery delay | 0% | [13 empty] | 0 | 0 | 0
Performance Bonus | 0% | [13 empty] | 0 | 0 | 0
Tools Cost | 0% | [13 empty] | 0 | 0 | 0
Any Other | 0% | [13 empty] | 0 | 0 | 0
Total Rate | [14 empty] | 21.6 | 5632 | 20500.48
Project Phase | From Estimation Sheet | From Resource Plan | Difference | Start Column | End Column | Comments
Total Dev Hrs | 1453.3333 | 120 | 1333.3333 | H9 | M13
Total QA Hrs | 385.7894 | 0 | 385.7894 | F14 | O14
Requirement | 84 | 96 | -12 | D7 | E16
Architecture | 58 | 0 | 58 | F8 | G8
HLD | 80 | 0 | 80 | F8 | G8
LLD | 0 | 0 | 0 | F8 | G8
Development | 125 | 120 | 5 | H7 | O13
Deployment | 72 | 0 | 72 | O7 | O17
Grand Total | 2258.1227 | 216
Onsite Expense(Travel and Accomodation)
Name of Expense/ Allowances | Rate Per Day($) | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Total Onsite Days |  | Cost USD | Cost QR
Onsite Allowance | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Accomodation | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Travel | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Total Onsite Expense | [15 empty] | 0 | 0
Other Expenses | bar: Wk 1 to Wk 4
Name of Expense | Quantity Type | Wk 1: Quantity; Wk 2: Rate USD; Wk 3: Cost USD; Wk 4: Cost QR
Training | Hours | Wk 1: 0; Wk 2: 0; Wk 3: 0; Wk 4: 0; Wk 7: Total Days; Wk 10: 27
Device Availability | Hours | Wk 1: 0; Wk 2: 0; Wk 3: 0; Wk 4: 0; Wk 7: Grand Total Cost; Wk 10: USD; Wk 12: INR
External Vendors | Hours | Wk 1: 0; Wk 2: 0; Wk 3: 0; Wk 4: 0; Wk 10: 5632; Wk 12: 20500.48
Additional Expenses 1 | Hours | Wk 1: 0; Wk 2: 0; Wk 3: 0; Wk 4: 0
Additional Expenses 2 | Hours | Wk 1: 0; Wk 2: 0; Wk 3: 0; Wk 4: 0
Total Other Expenses |  | Wk 3: 0; Wk 4: 0
**Referenced from QP Website
Note on C6: Author: This column rates will be filled by Finance Team. Proposal team to put the resources and hand over to Finance.

## S&D - Websites
Activity | Deliverable | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Initiation, Planning & Requirement
Project Kick-off | Kick-off Meeting and Meeting Minutes | bar: W1 to W12
Project Planning | Project Plan | bar: W1 to W12
Requirement Analysis | Requirement Gathering Document | bar: W1 to W12
Concept Finalization | Concept and SiteMap Documentation | bar: W1 to W12
Designing
Low Fidelity Design (Mock up) | All website pages clickable wireframes | bar: W1 to W12
High Fidelity Design (layout Design) | All Website pages final visual designs - 2 alternate designs Assets | bar: W1 to W12
Development
Iteration 1 | Code & Deployment Report | bar: W1 to W12
Iteration 2 | Code & Deployment Report | bar: W1 to W12
Iteration 3 | Code & Deployment Report | bar: W1 to W12
Deployment & Acceptance
Prodution Deployment | Code & Deployment Report | bar: W1 to W12
UAT & Signoff | UAT Acceptance | bar: W1 to W12
Go Live | bar: W1 to W12
PMO Activities
Regular project review and update meeting | MOMs | bar: W1 to W12
Status Reporting | Weekly project status report | bar: W1 to W12
Warranty
Maintenance & Support

## S&D - Mobile App
| Month -> |  |  |  | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M3 |  |  |  | M4
Sprint # | Phase | Activity | Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Planning
| Planning | Project Kick-off | Kick-off Meeting and Meeting Minutes Project Plan Communication Plan | bar: 1
2 | Requirements & Design Phase
| Requirements & Design | Requirement Fianlization and Wireframe designs | Functional Requirements Story List Product Backlog Architecture Diagram Wireframes & Screen Designs (By Client) Development Iteration Plan | bar: M1 2 to M1 3
Development Phase
3 | Iteration Development 1 | bar: 1 to M4 16
| Development | Software development and unit testing | Source Code
| Testing | Prepare Acceptance Test Criteria | UAT Test Case
| Testing | Testing of Iteration Release | Test Report
| Deployment | Deploy the iteration deliverables on the UAT/ Demo environment | Iteration Release and Client Demo
| Development | Incorporate client feedbacks | Iteration Release Feedback Report
4 | Iteration Development 2 | bar: 1 to M4 16
5 | Iteration Development 3 | bar: 1 to M4 16
6 | Deployment & AcceptancePhase
| UAT | Deploy in UAT/Production environment | Product release | bar: M3 10
| UAT | Present/demo the application module | Client Demo Meeting | bar: M3 10
| Closure | Project Acceptance | Project Acceptance Letter Sign off | bar: M3 10
Other Deliverables
| Project Management | Regular project review and update meeting | Meeting and MoM | bar: 1 to M3 10
| Project Management | Weekly project status report | Status Report | bar: 1 to M3 10

## S&D - Apps(Large)
| Month -> |  |  |  | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  | M6
# | Phase | Activity | Deliverable
1 | Planning
1.1 | Planning | Project Kick-off | Kick-off Meeting and Meeting Minutes | x
1.2 | Planning | Prepare Project Charter: | Project Charter | x
1.3 | Planning | Project Plan | Project Plan | x | x
1.4 | Planning | Prepare Quality Assurance Plan | Quality Assurance Plan | x | x | x
1.5 | Planning | Prepare Project Management Plan - The project management procedures, - Roles and responsibilities - Change management plan, - Communications plan, - Risk management plan, - System Installation Plan, - Business process improvement plan, - System implementation plan, - System testing plan, Training plan | Project Management Plan |  | x | x
2 | Requirements Phase
2.1 | Requirements | Detailed Requirements Gathering and analysis a) Functionality (Including Screen Prototype) b) External Interfaces c) Performance d) Characteristics e) Use and Misuse Cases f) Specification of the integration g) Requirements Traceability Matrix | Software Requirement Specification (SRS) |  | x | x | x
3 | Architecture & Design
3.1 | Architecture | Prepare Solution Architecture and High Level Design | Architecture Document with High level design |  | x | x | x
3.2 | Design | Prepare Detailed Design Document | Solution Design Document inlcuding UI Design |  | x | x | x
3.3 | Design | Prepare Test Plan and Test Scenarios | Test Plan Document |  | x | x | x
3.4 | Design | Development Iteration Planning | Development Iteration Plan |  |  | x | x
4 | Development Phase
Iteration Development 1
4.1 | Development | Software development and unit testing | Source Code | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
4.2 | Testing | Prepare Acceptance Test Criteria | UAT Test Case | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
4.3 | Testing | Testing of Iteration Release | Test Report
4.4 | Deployment | Deploy the iteration deliverables on the UAT/ Demo environment | Iteration Release and Client Demo | [9 empty] | x |  |  |  | x |  |  |  |  | x
4.5 | Development | Incorporate client feedbacks | Iteration Release Feedback Report | [16 empty] | x | x
Iteration Development 2
4.6 | Testing | System Testing | Defect Summary and Test Reports | [15 empty] | x | x | x
Documentation
4.7 | Documentation | Preparation of technical documentation and user manuals | Implementation Manual | [16 empty] | x | x
4.8 | Documentation | Preparation of technical documentation and user manuals | User Manual | [16 empty] | x | x
5 | Deployment & AcceptancePhase
5.1 | UAT | Deploy in UAT/Demo environment | Alpha release | [17 empty] | x | x
5.2 | UAT | Present/demo the application module | Client Demo Meeting | [17 empty] | x | x
5.3 | UAT | Incorporation of client feedback | UAT Report | [17 empty] | x | x
5.4 | Deployment | Server software installation and server configuration | Production Servers Ready | [12 empty] | x | x
5.5 | Deployment | Modules installed on server and configured | Applications Production Ready | [13 empty] | x
5.6 | Deployment | Servers regression tested and released for production | Beta Release, Release Notes, Installation and deployment plan | [13 empty] | x
5.7 | Training & KT | Module and user group level training plans prepared | Training Plan | [14 empty] | x | x
5.8 | Training & KT | Training various user groups | Training Sessions | [16 empty] | x | x
5.9 | Closure | Inititate Project Closure report | Project Closure Report | [19 empty] | x
5.10 | Closure | Project Acceptance | Project Acceptance Letter Sign off | [19 empty] | x
6 | Maintenance Phase
6.1 | Maintenance | Monthly project status report detailing support information, operational malfunctions, actions taken etc., | Monthly Status Report
6.2 | Maintenance | Defect fixes, performance tuning, monitoring | Patch Deployment
6.3 | Maintenance | Preventive Maintainanace (once in 6 months) | Maintenance Reports
7 | Other Deliverables
7.1 | Project Management | Regular project review and update meeting | Meeting and MoM | x | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x | x | x
7.2 | Project Management | Weekly project status report | Status Report, | x | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x | x | x
7.3 | Project Management | Monthly Progress Reports | Monthly progress reports |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x
7.4 | Project Management | Update Project Plan Based on the progress of the report | Project Plan Updates
7.5 | Project Management | Maintain Risk Log | Risk Log
7.6 | Project Management | Maintain Issue Log | Issue Log
**Referenced from 'DTA Mobile'

## S&D - PES
Stage | Phases | Activities | Activity Details | Deliverables | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | Naico Resource
[5 empty] | 0 | 0
Prototype / Alpha Version | Phase 1 (Proof of Concept) | Project Kick-Off |  | MOM
|  | Project Planning |  | Project Management Plan Quality Plan Certification Process Plan (High Level)
|  | Requirements freeze |  | Requirement Document
|  | Architecture |  | Architecture Document
Product Architecture
|  |  | Mechanical Architecture | Mechanical Architecture
Firmware Architecture
Cloud / Application Architecture
|  | Hardware BOM |  | Hardware BOM
|  | POC Demonstration |  | Proof of Concept Demo
| Phase 2 (Design) |  |  |  | W3: 0; W4: 0; W5: 0
|  | Develop Housing |  | Housing
BOM
|  |  | Electrical BOM | Electrical BOM
|  |  | Mechanical BOM | Mechanical BOM
|  | HW Schematic/PCB design |  | Schematic & PCB Designs, Gerber
|  | Application Screens Design | (If any)
Phase 3 (Prototype Build)
|  | Fab & Assembly (Iteration 1) |  | X Units for internal Testing Updated BOM
Procurement/fab/proto build
PCB Assembly
|  | Firmware Development |  | Firmware Code
Application Development
(if any)
|  | Functional Testing of X Units |  | X Units tested
Board Bring up
Software Bring Up
Functional Test Devices
System / Integration Test
|  | Fab & Assembly (Iteration 2) |  | X Units
Respin of the Board
Build devices
PCB Assembly
Application Development (Contd..)
|  |  | Cloud / iOT components | Code & Cloud Deployment
Create simulated devices on iOT(if any)
|  |  | Mobile Application Development(if any) | iOS Build + Android Build (Remaining Features)
Alexa Integration(if any)
|  | Testing of X Units(Iteration 2) |  | X Assembled Units Tested Cloud Platform Ready
Functional Test Devices
System / Integration Test
Other Deliverables
|  |  | Update Mechanical Drawings | Mechanical Drawings
|  |  | Update Electrical Drawings | Electrical Drawings
|  |  | Update BOM | BOM
|  | Phase 3 Wrap Up | Phase level Acceptance | Phase 4 Plan
Phase 4 is not estimated or not detailed out
Production go-To-market Product | Phase 4 (Production Ready Phase)
User Testing and Feedback
User Testing and Feedback
|  |  | Feedback Integration | Updated artifacts, code, devices
Load Testing
|  |  | Set up a load test environment | Load test environment Ready
Generate Simulated Devices for the load
|  |  | Load test | Load test report
Production System Provisioning
Production Hardware Provisioning
|  |  | Cloud Infrastructure Provisioning | Cloud infrastructure proposal
Application Development
|  |  | (if any feedback from Phase 3) | Code & Cloud Deployment

## Lookups
Adjustment factor lookups - All values in %
Database Used |  | Programming language used |  | Backend Platform used |  | Frontend Platform used |  | ORM used |  | ResourcePlanning Period
MS-Sql | 0 | C# | 0 | .Net | 0 | ASP.Net | 0 | None | 0 | Wk | Week
MySql | 0 | VB.net | 0 | PHP | 0 | Flex | 30 | Nhibernate | 0 | Mon | Month
Oracle | 0 | PHP | 0 | NodeJS | 5 | PHP | 0 | Naico ORM | 0
Access | 5 | C | 0 |  |  | MVC | 0 | Fluent Nhibernate | 5
MongoDB | 5 | Python | 5 |  |  | Angular | 0 | LinQ | 5
CouchDB | 5 |  |  |  |  | ReactJS | 5 | Dapper | 0
[6 empty] | VueJS | 5
Frontend architecture used |  | Backend architecture used |  | Overall architecture complexity |  | Distributed environment factor |  | Maximum concurrent users |  | ResourcePlanning Currency
ASP.Net / MVC | 0 | 3 Tier | 0 | Low | 0 | Low | 0 | 0-50 | 0 | AED | 3.67
Pure JS | 0 | Serive Oriented | 0 | Medium | 5 | Medium | 5 | 51-100 | 5 | INR | 65
JS SinglePage | 0 | Microservice | 0 | High | 10 | High | 10 | 101+ | 10 | QR | 3.64
|  | Cloud | 0 | Very High | 15 | Very High | 15 |  |  | SR | 3.75
Performance Requirements Complexity |  | Data Processing Complexity |  | Scalability Requirements |  | Deployment/Installation Requirements |  | Documentation Requirements Complexity |  | Localization required?
Low | 0 | Low | 0 | Low | 0 | Low | 0 | Low | 0 | No localization | 0
Medium | 0 | Medium | 5 | Medium | 0 | Medium | 5 | Medium | 5 | Static content | 5
High | 5 | High | 10 | High | 5 | High | 10 | High | 10 | Dynamic content | 10
Very High | 10 | Very High | 15 | Very High | 10 | Very High | 15 | Very High | 15
End user expertise level |  | Point of Contact Expertise level |  | Third party components used (eg. EXT.Net, JASON) |  | Browser compatibility |  | Remote dependency complexity |  | Mobile application platform
Low | 5 | Low | 10 | Nil | 0 | IE, Firefox, Chrome, Safari - Latest versions | 0 | Low | 0 | NA | 0
Medium | 0 | Medium | 5 | Telerik | 5 | Additional browser requirement | 5 | Medium | 5 | Android | 5
High | 0 | High | 0 | EXT.Net | 10 |  |  | High | 10 | iOS | 5
Very High | 0 | Very High | 0 | jQuery | 0 |  |  | Very High | 15 | PhoneGap | 5
[10 empty] | ReactNative | 10
Number of environments maintained |  | GIS development platform |  | Estimation - Size | Complexity | Estimation - Complexity |  | Estimation - Risk & Uncertainity |  | Right to Left Orientation
1-3 | 0 | NA | 0 | Extra Small | 2 | Normal | 1 | Normal | 1 | Yes | 10
4-5 | 5 | ArcGIS Server JS API | 5 | Small | 4 | Medium | 1.25 | Medium | 1.25 | No | 0
5+ | 10 | ArcGIS Server Silverlight API | 5 | Medium | 8 | High | 1.5 | High | 1.5
|  | OpenLayers | 10 | Large | 12 | Extreme | 2 | Extreme | 2
|  |  |  | Extra Large | 20
Estimation QA - Func Test Prep | Complexity | Estimation QA - Func Test Exec | Complexity | Estimation QA - Int Test Prep | Complexity | Estimation QA - Int Test Exec | Complexity | Estimation QA - Sys Test Prep | Complexity | Estimation QA - Int Test Exec | Complexity
Low | 0.16667 | Low | 0.11667 | Low | 0.083333 | Low | 0.083333 | Low | 0.083333 | Low | 0.083333
Medium | 0.2 | Medium | 0.25 | Medium | 0.083333 | Medium | 0.16667 | Medium | 0.083333 | Medium | 0.16667
High | 0.33333 | High | 0.5 | High | 0.16667 | High | 0.33333 | High | 0.16667 | High | 0.33333
Estimation QA - Reg Test Exec | Complexity |  |  | Estimation QA - Cycle Count |  | Project Type
Low | 0.083333 |  |  | Integration | 3 | Micro | 1000
Medium | 0.083333 |  |  | System | 2 | Small | 4000
High | 0.16667 |  |  | Client Feedbacks | 5 | Medium | 10000
|  |  |  | Regression Testing | 5 | Large | 10001
Micro |  | Small |  | Meduim |  | ResourcePlanning Period
Integration | 3 | Integration | 4 | Integration | 6 | Wk | Week
System | 2 | System | 3 | System | 8 | Mon | Month
Client Feedbacks | 5 | Client Feedbacks | 7 | Client Feedbacks | 10
Regression Testing | 5 | Regression Testing | 7 | Regression Testing | 10
ResourcePlanning Currency |  | Quantity Type
AED | 3.67 | Hours
INR | 65 | Count
QR | 3.64 | Lump Sum
SR | 3.75

## Overheads
[15 empty] | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  |  | M6
Estimation Overheads |  | Requirement | Micro |  |  | Small |  |  |  | Medium |  |  |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
Project Type | Small |  | Default | Custom | Final |  | Default | Custom | Final |  | Default | Custom | Final | Micro | M1 W1: Req; M1 W3: LLD; M2 W5: Development & Deployment
Overheads | Hrs | PM | 80 |  | 80 | PM | 10 |  | 10 | PM | 80 |  | 80 | Small | M1 W1: Req; M1 W4: HLD; M2 W5: LLD; M2 W7: Development & Deployment
Requirement | 84 | BA | 16 |  | 16 | BA | 24 |  | 24 | BA | 80 |  | 80 | Medium | M1 W1: Req; M2 W5: Arc; M2 W7: HLD; M3 W9: LLD; M3 W11: Development & Deployment
Architucture | 58 | TM | 0 |  | 0 | TM | 10 |  | 10 | TM | 0 |  | 0
HLD | 80 | Architect | 0 |  | 0 | Architect | 0 |  | 0 | Architect | 32 |  | 32 | Micro | M1 W1: PM; M1 W2: BA; M1 W3: Arch; M1 W4: PL/TL; M2 W5: Rev
LLD | 0 |  |  |  | 0 | Sr. Dev | 40 |  | 40 |  |  |  | 0 | Req | M1 W1: 100%; M1 W2: 20%; M2 W5: 5%
Development | 125 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | LLD | M1 W1: 50%; M1 W2: 10%; M1 W4: 50%; M2 W5: 5%
Deployment | 72 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | Development | M1 W1: 20%; M1 W4: 20%; M2 W5: 5%
| 419 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | Deployment | M1 W1: 5%; M1 W4: 100%; M2 W6: Considering 4 days deployment
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | Small | M1 W1: PM; M1 W2: BA; M1 W3: Arch; M1 W4: PL/TL; M2 W5: Rev
[14 empty] | Req | M1 W1: 80%; M1 W2: 50%; M1 W3: 10%; M1 W4: 10%; M2 W5: 5%
|  | Architucture | Micro |  |  | Small |  |  |  | Medium |  |  |  | HLD | M1 W1: 50%; M1 W2: 20%; M1 W3: 30%; M1 W4: 10%; M2 W5: 5%
|  |  | Default | Custom | Final |  | Default | Custom | Final |  | Default | Custom | Final | LLD | M1 W1: 50%; M1 W2: 10%; M1 W3: 20%; M1 W4: 20%; M2 W5: 5%
|  | PM | 0 |  | 0 | PM | 10 |  | 10 | PM | 24 |  | 24 | Development | M1 W1: 20%; M1 W3: 5%; M1 W4: 20%; M2 W5: 5%
|  | BA | 0 |  | 0 | BA | 0 |  | 0 | BA | 0 |  | 0 | Deployment | M1 W1: 5%; M1 W4: 100%; M2 W6: Considering 5 days deployment
|  | TM | 0 |  | 0 | TM | 0 |  | 0 | TM | 0 |  | 0
|  | Architect | 0 |  | 0 | Architect | 24 |  | 24 | Architect | 40 |  | 40 | Medium | M1 W1: PM; M1 W2: BA; M1 W3: Arch; M1 W4: PL/TL; M2 W5: Rev
[5 empty] | 0 | Sr. Dev | 24 |  | 24 |  |  |  | 0 | Req | M1 W1: 50%; M1 W2: 50%; M1 W3: 20%; M1 W4: 20%; M2 W5: 5%
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | Arc | M1 W1: 30%; M1 W2: 0%; M1 W3: 50%; M1 W4: 10%; M2 W5: 2%
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | HLD | M1 W1: 30%; M1 W2: 20%; M1 W3: 30%; M1 W4: 20%; M2 W5: 5%
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | LLD | M1 W1: 30%; M1 W2: 10%; M1 W3: 20%; M1 W4: 30%; M2 W5: 5%
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | Development | M1 W1: 20%; M1 W3: 5%; M1 W4: 20%; M2 W5: 5%
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | Deployment | M1 W1: 5%; M1 W4: 100%; M2 W6: Considering 7 days deployment
|  | HLD | Micro |  |  | Small |  |  |  | Medium
|  |  | Default | Custom | Final |  | Default | Custom | Final |  | Default | Custom | Final
|  | PM | 0 |  | 0 | PM | 10 |  | 10 | PM | 24 |  | 24
|  | BA | 0 |  | 0 | BA | 0 |  | 0 | BA | 16 |  | 16
|  | TM | 0 |  | 0 | TM | 0 |  | 0 | TM | 0 |  | 0
|  | Architect | 0 |  | 0 | Architect | 10 |  | 10 | Architect | 24 |  | 24
[5 empty] | 0 | Sr. Dev | 60 |  | 60 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
|  | LLD | Micro |  |  | Small |  |  |  | Medium
|  |  | Default | Custom | Final |  | Default | Custom | Final |  | Default | Custom | Final
|  | PM | 40 |  | 40 | PM | 0 |  | 0 | PM | 24 |  | 24
|  | BA | 8 |  | 8 | BA | 0 |  | 0 | BA | 8 |  | 8
|  | TM | 0 |  | 0 | TM | 0 |  | 0 | TM | 0 |  | 0
|  | Architect | 0 |  | 0 | Architect | 0 |  | 0 | Architect | 16 |  | 16
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
|  | Development | Micro |  |  | Small |  |  |  | Medium
|  |  | Default | Custom | Final |  | Default | Custom | Final |  | Default | Custom | Final
|  | PM | 64 |  | 64 | PM | 90 |  | 90 | PM | 112 |  | 112
|  | BA | 0 |  | 0 | BA | 0 |  | 0 | BA | 0 |  | 0
|  | TM | 0 |  | 0 | TM | 15 |  | 15 | TM | 0 |  | 0
|  | Architect | 0 |  | 0 | Architect | 20 |  | 20 | Architect | 28 |  | 28
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
|  | Deployment | Micro |  |  | Small |  |  |  | Medium
|  |  | Default | Custom | Final |  | Default | Custom | Final |  | Default | Custom | Final
|  | PM | 2 |  | 2 | PM | 8 |  | 8 | PM | 3 |  | 3
|  | BA | 0 |  | 0 | BA | 0 |  | 0 | BA | 0 |  | 0
|  | TM | 0 |  | 0 | TM | 0 |  | 0 | TM | 0 |  | 0
|  | Architect | 0 |  | 0 | Architect | 0 |  | 0 | Architect | 0 |  | 0
[5 empty] | 0 | Sr. Dev | 64 |  | 64 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0

## AdjustmentFactor
Estimation Adjustment Factor
Adjustment Factor | Naico Standards | Parameter | Adjustment Factor %
Database Used | MSSQL,MySQL | MS-Sql | 0
Programming language used | C# , PHP | C# | 0
Backend Platform Used | ASP.Net, PHP | NodeJS | 5
Front end Platform Used | ASP.Net, PHP, Flex | ASP.Net | 0
ORM Tool used | Nhibernate, Naico ORM | Dapper | 0
Front end Architectures Used | HTML and Flex Flurine Cairncong-25% | Pure JS | 0
Server side Architecture Used | ASP.Net MVC2 | 3 Tier | 0
Overall Architecture Complexity |  | Low | 0
Distributed Environment Factor Complexity | Multiple server deployment eg.AflexDoc | Low | 0
Maximum cuncurrent users | 0-50,51-100,101+ | 0-50 | 0
Performance Requirements | Based on client requirements | Low | 0
Data Processing Complexity |  | Low | 0
Scalability Requirements | Based on client requirements eg. Ease of new feature addion, integration with related systems etc. | Low | 0
Deployment Requirements | Based on client requirements | Low | 0
Documentation Requirements | Project Plan, Test plan, Tracebility Matrix, Installation notes, Delivery Walk throughs (Help documents etc) | Low | 0
End User Expertise Level |  | Medium | 0
Point of Contact Expertise level |  | High | 0
Third party components used (eg. EXT.Net, JASON) |  | Nil | 0
Browser compatibility |  | IE, Firefox, Chrome, Safari - Latest versions | 0
Remote dependency factor | Eg. Ivincci (accessing St. Luke servers) | Low | 0
Number of environments maintained | Dev, QA, Stage, Production, Client | 1-3 | 0
Localization required? | Support for other languages | Dynamic content | 10
Right to Left Orientation Support | Support for RTL | No | 0
Mobile application platform |  | NA | 0
GIS development platform |  | NA | 0
Function Point Adjustment Factor |  |  | 15
Note on B3: Author: Factors infulencing entire project. Implemtnetion of payment gate way or Google API integration not considered here as they not impact over all project.
Note on C5: Author: Standard items will have 0% additional impact

## Weightages
UI Functionalities Weightage
Simple Controls | 0.5
Medium Complex Controls | 2
High Complex Controls | 4
Data Field Queries | 1
Table Queries | 1.5
Simple Search Fields | 1
Complex Search Fields | 3
Web Page Implementation Weightage |  | Data Base Design Weightage
Content Boxes | 1 | Data Fields | 0.1
Banners | 1.5 | Simple Tables | 0.25
Animations | 2 | Mid Complex Tables | 1
Graphical Images | 1.5 | High Complex Tables | 2
Forms | 2
Average fields in a form | 1
Simple Menu | 1
Complex Menu | 1.5
DB Queries | 1.5