## MKC Project Plan
PROJECT |  |  | START DATE
MKC WIRAS Monitoring Solution |  |  | 2022-01-03
User to complete non-shaded fields only. | [6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20 |  |  |  |  | Wk21 |  |  |  |  | Wk 22 |  |  |  |  | Wk23 |  |  |  |  | Wk 24
TASKS | TASK OWNER | STATUS | START DATE | END DATE | HRS | DAYS | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | STATUS
Phase 1 - Requirement gathering & Design |  |  | 2022-01-03 | 2022-01-28 |  | 20 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | [100 empty] | Not Started
Requirement gathering | PM | Complete | 2022-01-03 | 2022-01-14 |  | 10 | A | A | A | A | A | A | A | A | A | A | [110 empty] | In Progress
High Level Design | Architect | Complete | 2022-01-17 | 2022-01-28 |  | 10 | [10 empty] | A | A | A | A | A | A | A | A | A | A | [100 empty] | Complete
Phase 2 - Application Development |  |  | 2022-01-31 | 2022-03-11 |  | 30 | [20 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | [70 empty] | Needs Update
Development Sprint 1 | Dev/QC Team | Complete | 2022-01-31 | 2022-02-11 |  | 10 | [20 empty] | A | A | A | A | A | A | A | A | A | A | [90 empty] | Canceled
Development Sprint 2 | Dev/QC Team | Complete | 2022-02-14 | 2022-02-25 |  | 10 | [30 empty] | A | A | A | A | A | A | A | A | A | A
Development Sprint 3 | Dev/QC Team | Complete | 2022-02-28 | 2022-03-11 |  | 10 | [40 empty] | A | A | A | A | A | A | A | A | A | A
Phase 2 - Hardware Procurement and Intergration |  |  | 2022-03-14 | 2022-05-20 |  | 50 | [50 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Web App system testing and bug fixing | Dev/QC Team | Complete | 2022-03-14 | 2022-03-25 |  | 10 | [50 empty] | A | A | A | A | A | A | A | A | A | A
Hardware Procurement | Naico - PM | In Progress | 2022-03-28 | 2022-05-20 |  | 40 | [60 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Feasibility study with Rasberry Pie | Embedded Dev | Complete | 2022-04-20 | 2022-04-26 |  | 5
Brining Up the devide and Santy Check - Energy Meter
Activity 1 - Checking the working of Device |  | Complete | 2022-04-07 | 2022-04-07 |  | 1 | [68 empty] | A
Task 1 - Checking the working of Device |  | Complete | 2022-04-07 | 2022-04-07 |  | 1 | [68 empty] | A
Sub Task 1 - Connecting the power source checking the load | Embedded Dev | Complete | 2022-04-07 | 2022-04-07 | 5 | 1
Activity 2 - Communication with System and Device via RS-485 (Getting proper data and vailidation) |  | Complete | 2022-04-11 | 2022-04-13 |  | 3 | [70 empty] | A | A | A
Task 1 - Communication with System and Device via RS-485 | Embedded Dev | Complete | 2022-04-11 | 2022-04-11 | 8 | 1
Task 2 - Command configuration (Request) | Embedded Dev | Complete | 2022-04-12 | 2022-04-12 | 8 | 1
Task 3 - Response from device and data extraction | Embedded Dev | Complete | 2022-04-13 | 2022-04-13 | 8 | 1
Activity 3 - RS-485 communication and integration with Rasberry Pie |  | Complete | 2022-04-20 | 2022-04-22 |  | 3
Task 1 - Establishing TCP/IP connection establishment | Embedded Dev | Complete | 2022-04-20 | 2022-04-20 | 4 | 1
Task 2 - Devloping Python code to read data from gateway | Embedded Dev | Complete | 2022-04-21 | 2022-04-21 | 8 | 1
Task 3 - Establishing request and response usgin Python Code | Embedded Dev | Complete | 2022-04-21 | 2022-04-22 | 12 | 2
Activity 4 - Two way communication between Pie and IoT hub |  | In Progress | 2022-04-25 | 2022-05-13 |  | 15
Task 1 - Establishing request to IoT hub |  | In Progress |  |  |  | 0
Sub Task 1 - Reading the request and processing it | Embedded Dev | Not Started | 2022-05-05 | 2022-05-05 | 4 | 1
Sub Task 2 - Sending request from Azure Function | App Dev | Not Started | 2022-05-06 | 2022-05-06 | 8 | 1
Task 2 - Establishing Response from Pie to IoT hub |  | Not Started |  |  |  | 0
Sub Task 1 - Sending request and processing it | Embedded Dev | Not Started | 2022-05-09 | 2022-05-10 | 12 | 2
Sub Task 2 - Reading the request and processing it | App Dev | Not Started | 2022-05-10 | 2022-05-11 | 12 | 2
Activity 5 - Intergration of ioT device with Web App |  | Not Started | 2022-05-11 | 2022-05-12 |  | 2
Task 1 - Reading Data from IoT hub to DB |  | Not Started |  |  |  | 0
Sub Task 1 - Checking Azure function and updating time series Mongo DB | App Dev | Not Started | 2022-05-11 | 2022-05-11 | 8 | 1
Sub Task 2 - Verification of Azure Function and updating Postgress DB | App Dev | Not Started | 2022-05-12 | 2022-05-12 | 8 | 1
Activity 6 - App developer variying the data in Web App Dashboard |  | Not Started | 2022-05-13 | 2022-05-16 |  | 2
Task 1 - Making sure data from Postgress DB is fetching properly | App Dev | Not Started | 2022-05-13 | 2022-05-16 | 10 | 2
Task 2 - Verifying the appropriate graph and making sure the accuracy of data | App Dev | Not Started | 2022-05-16 | 2022-05-16 | 8 | 1
Brining Up the devide and Santy Check - Flowmeter | Embedded Dev | In Progress |  |  |  | 0
Activity 1 - Checking the working of Device |  | Not Started |  |  |  | 0
Task 1 - Checking the working of Device |  | Not Started |  |  |  | 0
Sub Task 1 - Connecting the power source and checking if it is working fine | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Verifying if the device is reading fine based on water flow through flowmeter | Embedded Dev | Not Started |  |  |  | 0
Eternal Dependencies 1 - Weight of flowmeter and possibility of installing the samein customer premises | Embedded Dev | Not Started |  |  |  | 0
Internal Dependencies 1 - Need to purchase either force Nozzle or small motor to verify the water flow through flowmeter | Embedded Dev | Not Started |  |  |  | 0
Internal Dependencies 2 - Getting a developer to verify the Web App with adequate data received | Embedded Dev | Not Started |  |  |  | 0
Activity 2 - Communication with System and Device via RS-485 (Getting proper data and vailidation) |  | Not Started |  |  |  | 0
Task 1 - Communication with System and Device via RS-485 | Embedded Dev | Not Started |  |  |  | 0
Task 2 - Command configuration (Request) | Embedded Dev | Not Started |  |  |  | 0
Task 3 - Response from device and data extraction | Embedded Dev | Not Started |  |  |  | 0
Activity 3 - RS-485 communication and integration with Rasberry Pie |  | Not Started |  |  |  | 0
Task 1 - Establishing TCP/IP connection establishment | Embedded Dev | Not Started |  |  |  | 0
Task 2 - Devloping Python code to read data from gateway | Embedded Dev | Not Started |  |  |  | 0
Task 3 - Establishing request and response usgin Python Code | Embedded Dev | Not Started |  |  |  | 0
Activity 4 - Two way communication between Pie and IoT hub |  | Not Started |  |  |  | 0
Task 1 - Establishing request to IoT hub |  | Not Started |  |  |  | 0
Sub Task 1 - Reading the request and processing it | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Sending request from Azure Function | App Dev | Not Started |  |  |  | 0
Task 2 - Establishing Response from Pie to IoT hub |  | Not Started |  |  |  | 0
Sub Task 1 - Sending request and processing it | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Reading the request and processing it | App Dev | Not Started |  |  |  | 0
Activity 5 - Intergration of ioT device with Web App |  | Not Started |  |  |  | 0
Task 1 - Reading Data from IoT hub to DB |  | Not Started |  |  |  | 0
Sub Task 1 - Checking Azure function and updating time series Mongo DB | App Dev | Not Started |  |  |  | 0
Sub Task 2 - Verification of Azure Function and updating Postgress DB | App Dev | Not Started |  |  |  | 0
Activity 6 - App developer variying the data in Web App Dashboard |  | Not Started |  |  |  | 0
Task 1 - Making sure data from Postgress DB is fetching properly | App Dev | Not Started |  |  |  | 0
Task 2 - Verifying the appropriate graph and making sure the accuracy of data | App Dev | Not Started |  |  |  | 0
Brining Up the devide and Santy Check - Waterlevel Sensor | [5 empty] | 0
Activity 1 - Checking the working of Device |  | Not Started |  |  |  | 0
Task 1 - Checking the working of Device |  | Not Started |  |  |  | 0
Sub Task 1 - Connecting the power source and checking if it is working fine | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Verifying if the device is reading fine based on wateR availability in the bucket | Embedded Dev | Not Started |  |  |  | 0
Internal Dependencies 1 - Getting a developer to verify the Web App with adequate data received | Embedded Dev | Not Started |  |  |  | 0
Activity 2 - Communication with System and Device via RS-485 (Getting proper data and vailidation) |  | Not Started |  |  |  | 0
Task 1 - Communication with System and Device via RS-485 | Embedded Dev | Not Started |  |  |  | 0
Task 2 - Command configuration (Request) | Embedded Dev | Not Started |  |  |  | 0
Task 3 - Response from device and data extraction | Embedded Dev | Not Started |  |  |  | 0
Activity 3 - RS-485 communication and integration with Rasberry Pie |  | Not Started |  |  |  | 0
Task 1 - Establishing TCP/IP connection establishment | Embedded Dev | Not Started |  |  |  | 0
Task 2 - Devloping Python code to read data from gateway | Embedded Dev | Not Started |  |  |  | 0
Task 3 - Establishing request and response usgin Python Code | Embedded Dev | Not Started |  |  |  | 0
Activity 4 - Two way communication between Pie and IoT hub |  | Not Started |  |  |  | 0
Task 1 - Establishing request to IoT hub |  | Not Started |  |  |  | 0
Sub Task 1 - Reading the request and processing it | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Sending request from Azure Function | App Dev | Not Started |  |  |  | 0
Task 2 - Establishing Response from Pie to IoT hub |  | Not Started |  |  |  | 0
Sub Task 1 - Sending request and processing it | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Reading the request and processing it | App Dev | Not Started |  |  |  | 0
Activity 5 - Intergration of ioT device with Web App |  | Not Started |  |  |  | 0
Task 1 - Reading Data from IoT hub to DB |  | Not Started |  |  |  | 0
Sub Task 1 - Checking Azure function and updating time series Mongo DB | App Dev | Not Started |  |  |  | 0
Sub Task 2 - Verification of Azure Function and updating Postgress DB | App Dev | Not Started |  |  |  | 0
Activity 6 - App developer variying the data in Web App Dashboard |  | Not Started |  |  |  | 0
Task 1 - Making sure data from Postgress DB is fetching properly | App Dev | Not Started |  |  |  | 0
Task 2 - Verifying the appropriate graph and making sure the accuracy of data | App Dev | Not Started |  |  |  | 0
Brining Up the devide and Santy Check - STP | [5 empty] | 0
Activity 1 - Checking the working of Device |  | Not Started |  |  |  | 0
Task 1 - Checking the working of Device |  | Not Started |  |  |  | 0
Sub Task 1 - Connecting the power source and checking if it is working fine | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Verifying if the device is reading fine based on quality of water in the bucket | Embedded Dev | Not Started |  |  |  | 0
Internal Dependencies 1 - Getting a developer to verify the Web App with adequate data received | Embedded Dev | Not Started |  |  |  | 0
External Dependencies 1 - Getting the devises on time after clearance | Embedded Dev | Not Started |  |  |  | 0
Activity 2 - Communication with System and Device via RS-485 (Getting proper data and vailidation) |  | Not Started |  |  |  | 0
Task 1 - Communication with System and Device via RS-485 | Embedded Dev | Not Started |  |  |  | 0
Task 2 - Command configuration (Request) | Embedded Dev | Not Started |  |  |  | 0
Task 3 - Response from device and data extraction | Embedded Dev | Not Started |  |  |  | 0
Activity 3 - RS-485 communication and integration with Rasberry Pie |  | Not Started |  |  |  | 0
Task 1 - Establishing TCP/IP connection establishment | Embedded Dev | Not Started |  |  |  | 0
Task 2 - Devloping Python code to read data from gateway | Embedded Dev | Not Started |  |  |  | 0
Task 3 - Establishing request and response usgin Python Code | Embedded Dev | Not Started |  |  |  | 0
Activity 4 - Two way communication between Pie and IoT hub |  | Not Started |  |  |  | 0
Task 1 - Establishing request to IoT hub |  | Not Started |  |  |  | 0
Sub Task 1 - Reading the request and processing it | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Sending request from Azure Function | App Dev | Not Started |  |  |  | 0
Task 2 - Establishing Response from Pie to IoT hub |  | Not Started |  |  |  | 0
Sub Task 1 - Sending request and processing it | Embedded Dev | Not Started |  |  |  | 0
Sub Task 2 - Reading the request and processing it | App Dev | Not Started |  |  |  | 0
Activity 5 - Intergration of ioT device with Web App |  | Not Started |  |  |  | 0
Task 1 - Reading Data from IoT hub to DB |  | Not Started |  |  |  | 0
Sub Task 1 - Checking Azure function and updating time series Mongo DB | App Dev | Not Started |  |  |  | 0
Sub Task 2 - Verification of Azure Function and updating Postgress DB | App Dev | Not Started |  |  |  | 0
Activity 6 - App developer variying the data in Web App Dashboard |  | Not Started |  |  |  | 0
Task 1 - Making sure data from Postgress DB is fetching properly | App Dev | Not Started |  |  |  | 0
Task 2 - Verifying the appropriate graph and making sure the accuracy of data | App Dev | Not Started |  |  |  | 0
Documentation on Implementation and maintanence | Dev Team | Not Started | 2022-05-02 | 2022-05-20 |  | 15 | [85 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Procurement of Industry Pie - Feasibility of Rasberry Pie |  | Not Started | 2022-05-02 | 2022-05-20 |  | 15 | [85 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Phase 3 - System Verification |  |  | 2022-05-16 | 2022-05-27 |  | 10 | [95 empty] | A | A | A | A | A | A | A | A | A | A
Verification of the system as per design - Energy Meter | Test Engineer | Not Started | 2022-05-16 | 2022-05-17 |  | 2 | [95 empty] | A | A
Verification of the system as per design - Flowmeter | Test Engineer | Not Started | 2022-05-18 | 2022-05-20 |  | 3 | [97 empty] | A | A | A
Verification of the system as per design - Water Level Sensor | Test Engineer | Not Started | 2022-05-23 | 2022-05-24 |  | 2 | [100 empty] | A | A
Verification of the system as per design - STP | Test Engineer | Not Started | 2022-05-25 | 2022-05-27 |  | 3 | [102 empty] | A | A | A
Phase 4 - System Validation |  |  | 2022-06-06 | 2022-06-10 |  | 5 | [110 empty] | A | A | A | A | A
Validating the system performance on premises - Energy Meter | Embedded Dev & Test Engineer | Not Started | 2022-05-30 | 2022-05-31 |  | 2 | [105 empty] | A | A
Validating the system performance on premises - Flowmeter | Embedded Dev & Test Engineer | Not Started | 2022-06-01 | 2022-06-03 |  | 3 | [107 empty] | A | A | A
Validating the system performance on premises - Water Level Sensor | Embedded Dev & Test Engineer | Not Started | 2022-06-06 | 2022-06-07 |  | 2 | [110 empty] | A | A
Validating the system performance on premises - STP | Embedded Dev & Test Engineer | Not Started | 2022-06-08 | 2022-06-10 |  | 3 | [112 empty] | A | A | A
Phase 5 - Rollout, Deployment Acceptance and Closure |  |  | 2022-06-06 | 2022-06-17 |  | 10 | [110 empty] | A | A | A | A | A | A | A | A | A | A
Providing training for MKC team on overall software user flow | Naico - PM & Dev Team | Not Started | 2022-06-06 | 2022-06-10 |  | 5 | [110 empty] | A | A | A | A | A
Approval from MKC team and Closure | MKC and Naico | Not Started | 2022-06-13 | 2022-06-17 |  | 5 | [115 empty] | A | A | A | A | A
Note on B130: This is basically for preparing user guide and future maintanance
Note on B133: Making sure harware purchased are working as expected
Note on B134: Making sure harware purchased are working as expected
Note on B135: Making sure harware purchased are working as expected
Note on B136: Making sure harware purchased are working as expected
Note on B138: Making sure devices are working fine after implementation
Note on B139: Making sure devices are working fine after implementation
Note on B140: Making sure devices are working fine after implementation
Note on B141: Making sure devices are working fine after implementation

## Dependencies
External Dependencies
Delay in Hardware Procurement - STP sensors are delaying than expected
Additional items required to complete one time testing of sensors and Flowmeters like Motor, Buckets, etc.
Possibility of implementing flowmeter in the customer premises due to its heavy weight
Possibility of how fast implementation can be done from customer end to complete entire system validation from customer end
Internal Dependencies
Availability of API developer to provide adequate knowledge trasfer to new resourse and corresponding learning curve
Web App integration and corresponding real time data update in Dashboards