## WeeklyStatusReport
MKC WIRAS Monitoring Solution Weekly Status Report for Jan 24 2022 to Jan 28 2022
Actual / Potential Risks to Project Cost and Schedule
S No | Risk Description |  | Risk Impact |  |  | Status | Naico Actions and Remarks
1 | Installation of power supply for Sensors and Edge devices |  | Long distance will have reduction in current which in turn will impact data passed to App |  |  | MITIGATED | Based on site visit, Naico will be providing a proper plan on the Installation details
2 | Identifying water level in Pond and Well |  | Identifying right sensors and installing it in right place to get proper water level |  |  | OPEN | Naico is currently getting quotes and installation details fom different vendors for checking water level, once the vendor is identified, proper installation will be identified 24/01 - Naico require some updates from MKC to complete the entire requirement of identifying water level
3 | Proper network availability near sensor installations |  | With current details collected, we need to have the network availability within 100 meters |  |  | MITIGATED | Based on site visit, if the ethernet connectivity is not possible in 100 meters, Naico will be finding alternate options and updating MKC accordingly 24/01 - Seems like there were near by buildings where ether net connectivity is possible
Activities Planned and Executed in the Last Week
Sl. No: | Activity Description | Start Date | End Date | Current Status | Remarks
1 | Identifying proper sensors | 2022-01-03 | 2022-01-28 | In Progress | This is being partially completed and final decision can be made after site visit 24/01 - Need to finalize the vendors or need to provide detailed documentation to MKC on Sensor purchase and installation. This activity will be completed by this week 31/01 - All the sensor infomrations being passed to MKC for procurement and waiting for the confirmtion from MKC
2 | Learning Sensor installations | 2022-01-03 | 2022-01-28 | In Progress | Completed and final decision will be made after site visit 24/01 - Naico is yet to get some updates on Water Connection diagrams and also data to validate water quantity. 31/01 - Waiting still for pipeline connection diagram and number of flowmeter to be used. All the sensor detils being passed to MKC, waiting for purchase and futher testing
3 | Identifying risks and doscumenting | 2022-01-03 | 2022-01-13 | Open
4 | Preparing Project Plan | 2022-01-10 | 2022-01-28 | Closed | Completed
5 | Architectural Document Preperation and JIRA story updates | 2022-01-10 | 2022-01-28 | Closed | Completed
Activities Planned for This Week
Sl. No: | Planned Item Description | Start | End | Remarks
1 | Development Sprint 1 | 2022-01-31 | 2022-02-11 | Started and in progress
2 | Confirmation on Purchas of Vendors | 2022-01-31 | 2022-02-11 | Need to confirm in one week
Areas of Concern if any
Need to address the action itens send by Naico at the earliest Few action items pending from your end are, MKC team will give the depth of the dam by measuring the diameter and length/breadth as and when required. MKC team needs to give the plumbing diagram with the exact diameter of each pipe, which needs to be used to identify the number of Flow Meter. If we need to get the water consumption by facilities like Hostel, Admin and Class Room, then detailed plumbing diagram is required MKC team must set a tank in the outlet of the STP plant. The STP sensors need to dip in the tank. MKC team will arrange a meeting with the third party who will procure and implement the hardware part.
Other Communications if any (Upcoming Naico Holidays, Lead's Upcoming Leave Plan etc.)
Project Milestone Summary (If project duration more than 3 months list the milestones targeted for next 3 months)
Sl. No: | Milestone Description | Planned Date | Revised Date | Actual Date | Status | Risk Level | Client Dependencies for the Milestone
1 | Requirement Gathering | 2022-01-14 |  |  | ON PLAN | HIGH
2 | Arichitucture Design | 2022-01-28 |  |  | ON PLAN | MEDIUM
3 | App Development Sprint 1 | 2022-02-11 |  |  | ON PLAN | MEDIUM
4 | App Development Sprint 2 | 2021-02-25 |  |  | ON PLAN | MEDIUM
5 | Set Up and System Integration | 2022-03-25 |  |  | ON PLAN | VERY HIGH | Need to be implemeted in client site
6 | System Testting | 2022-04-15 |  |  | ON PLAN | HIGH
7 | Deployment, Acceptance & Closure | 2022-04-29 |  |  | ON PLAN | NONE